## Primavera Schedule
SYNTHETIC PRIMAVERA L5/L6 SCHEDULE — JAMNAGAR REFINERY PROJECT
Disciplines: Civil (blue) ¦ Piping (green) ¦ Electrical (yellow) ¦ Instrumentation (orange) ¦ HSE (purple)
activity_id | activity_name | discipline | planned_start | planned_end | wbs_level
L5-CIVIL-2801 | Topographic survey and setting out Unit 5 | Civil | 2026-08-01 | 2026-08-03 | L5
L5-CIVIL-2802 | Excavation for pile cap grid A Unit 5 | Civil | 2026-08-03 | 2026-08-06 | L5
L5-CIVIL-2803 | Pile driving grid A Unit 5 | Civil | 2026-08-06 | 2026-08-10 | L5
L5-CIVIL-2804 | Reinforcement bar placement pile cap grid A Unit 5 | Civil | 2026-08-10 | 2026-08-12 | L5
L5-CIVIL-2805 | Concrete placement pile cap grid A Unit 5 | Civil | 2026-08-12 | 2026-08-14 | L5
L5-CIVIL-2806 | Formwork erection column grid A Unit 5 | Civil | 2026-08-14 | 2026-08-16 | L5
L5-CIVIL-2807 | Concrete placement columns grid A Unit 5 | Civil | 2026-08-16 | 2026-08-18 | L5
L5-CIVIL-2808 | Curing of concrete columns grid A Unit 5 | Civil | 2026-08-18 | 2026-08-21 | L5
L5-CIVIL-2809 | Backfilling and compaction grid A Unit 5 | Civil | 2026-08-21 | 2026-08-23 | L5
L5-CIVIL-2810 | Excavation for pile cap grid B Unit 6 | Civil | 2026-08-10 | 2026-08-13 | L5
L5-CIVIL-2811 | Pile driving grid B Unit 6 | Civil | 2026-08-13 | 2026-08-17 | L5
L5-CIVIL-2812 | Reinforcement bar placement pile cap grid B Unit 6 | Civil | 2026-08-17 | 2026-08-19 | L5
L5-CIVIL-2813 | Concrete placement pile cap grid B Unit 6 | Civil | 2026-08-19 | 2026-08-21 | L5
L5-CIVIL-2814 | Formwork erection column grid B Unit 6 | Civil | 2026-08-21 | 2026-08-23 | L5
L5-CIVIL-2815 | Concrete placement columns grid B Unit 6 | Civil | 2026-08-23 | 2026-08-25 | L5
L5-CIVIL-2816 | Curing of concrete columns grid B Unit 6 | Civil | 2026-08-25 | 2026-08-28 | L5
L5-CIVIL-2817 | Backfilling and compaction grid B Unit 6 | Civil | 2026-08-28 | 2026-08-30 | L5
L5-CIVIL-2818 | Road base course laying access road north | Civil | 2026-08-15 | 2026-08-20 | L5
L5-CIVIL-2819 | Asphalt wearing course access road north | Civil | 2026-08-20 | 2026-08-23 | L5
L5-CIVIL-2820 | Storm water drain construction Unit 5 perimeter | Civil | 2026-08-05 | 2026-08-12 | L5
L6-CIVIL-2841 | Setting out column centerlines grid C Unit 7 | Civil | 2026-08-25 | 2026-08-25 | L6
L6-CIVIL-2842 | Excavation column footing C-7/F-01 to C-7/F-06 | Civil | 2026-08-25 | 2026-08-27 | L6
L6-CIVIL-2843 | Reinforcement placement column footing C-7/F-01 to F-06 | Civil | 2026-08-27 | 2026-08-29 | L6
L6-CIVIL-2844 | Formwork fixing column footing C-7/F-01 to F-06 | Civil | 2026-08-29 | 2026-08-30 | L6
L6-CIVIL-2845 | Concrete pour column footing C-7/F-01 to F-06 | Civil | 2026-08-30 | 2026-08-31 | L6
L6-CIVIL-2846 | Deshuttering and curing footing C-7/F-01 to F-06 | Civil | 2026-08-31 | 2026-09-02 | L6
L6-CIVIL-2847 | Concrete placement column foundations C-7/F-12 to F-18 | Civil | 2026-09-01 | 2026-09-03 | L6
L6-CIVIL-2848 | Reinforcement bar placement column C-7/F-12 to F-18 | Civil | 2026-08-30 | 2026-09-01 | L6
L6-CIVIL-2849 | Backfilling column footing C-7/F-12 to F-18 | Civil | 2026-09-03 | 2026-09-04 | L6
L6-CIVIL-2850 | Anti-termite treatment Unit 7 foundation zone | Civil | 2026-09-04 | 2026-09-05 | L6
L5-PIPING-1101 | Pipe spool fabrication 6-inch CS lines Unit 5 | Piping | 2026-08-01 | 2026-08-10 | L5
L5-PIPING-1102 | Pipe spool fabrication 12-inch CS lines Unit 5 | Piping | 2026-08-05 | 2026-08-15 | L5
L5-PIPING-1103 | Pipe spool fabrication 24-inch lines north rack | Piping | 2026-08-08 | 2026-08-20 | L5
L5-PIPING-1104 | Hydrostatic pressure testing 6-inch lines Unit 5 | Piping | 2026-08-20 | 2026-08-23 | L5
L5-PIPING-1105 | Hydrostatic pressure testing 12-inch lines Unit 5 | Piping | 2026-08-22 | 2026-08-25 | L5
L5-PIPING-1106 | Radiographic examination weld joints Unit 5 | Piping | 2026-08-15 | 2026-08-22 | L5
L5-PIPING-1107 | Post weld heat treatment alloy lines Unit 5 | Piping | 2026-08-12 | 2026-08-18 | L5
L5-PIPING-1108 | Insulation and cladding hot lines Unit 5 | Piping | 2026-08-25 | 2026-09-02 | L5
L5-PIPING-1109 | Painting and coating piping Unit 5 | Piping | 2026-08-18 | 2026-08-26 | L5
L5-PIPING-1110 | Pipe rack structural erection north Unit 6 | Piping | 2026-08-10 | 2026-08-20 | L5
L6-PIPING-1191 | Erect spool 24-PL-0041 north rack elevation 4.5m | Piping | 2026-08-20 | 2026-08-21 | L6
L6-PIPING-1192 | Erect spool 24-PL-0043 north rack elevation 4.5m | Piping | 2026-08-21 | 2026-08-22 | L6
L6-PIPING-1193 | Erect spool 24-PL-0047 north rack elevation 7.5m | Piping | 2026-09-01 | 2026-09-02 | L6
L6-PIPING-1194 | Hydrostatic pressure test line 24-PL-0047 | Piping | 2026-09-03 | 2026-09-03 | L6
L6-PIPING-1195 | Weld joint inspection north rack elevation 7.5m | Piping | 2026-09-02 | 2026-09-02 | L6
L6-PIPING-1196 | Install pipe supports line 18-PL-0023 south rack | Piping | 2026-09-04 | 2026-09-05 | L6
L6-PIPING-1197 | Erect spool 18-PL-0023 south rack elevation 4.5m | Piping | 2026-09-05 | 2026-09-06 | L6
L6-PIPING-1198 | Radiographic test weld joint PL-0047-W-04 | Piping | 2026-09-02 | 2026-09-02 | L6
L6-PIPING-1199 | Flush and clean line 24-PL-0047 prior to hydrotest | Piping | 2026-09-02 | 2026-09-03 | L6
L6-PIPING-1200 | Gasket and bolting final assembly line 24-PL-0047 | Piping | 2026-09-03 | 2026-09-04 | L6
L5-ELEC-3301 | Low voltage cable laying MCC room B phase 1 | Electrical | 2026-08-15 | 2026-08-22 | L5
L5-ELEC-3302 | Low voltage cable laying MCC room B phase 2 | Electrical | 2026-08-22 | 2026-08-29 | L5
L5-ELEC-3303 | Earthing and bonding MCC room B | Electrical | 2026-08-29 | 2026-09-01 | L5
L5-ELEC-3304 | Cable tray installation Unit 7 east corridor | Electrical | 2026-08-10 | 2026-08-18 | L5
L5-ELEC-3305 | Cable tray installation Unit 7 west corridor | Electrical | 2026-08-18 | 2026-08-25 | L5
L5-ELEC-3306 | HV cable pulling transformer T-04 to switchgear | Electrical | 2026-08-20 | 2026-08-27 | L5
L5-ELEC-3307 | Termination of HV cables transformer T-04 | Electrical | 2026-08-27 | 2026-08-30 | L5
L5-ELEC-3308 | Testing and commissioning MCC room B panels | Electrical | 2026-09-01 | 2026-09-05 | L5
L5-ELEC-3309 | Street lighting installation north perimeter road | Electrical | 2026-08-12 | 2026-08-20 | L5
L5-ELEC-3310 | Motor control wiring pumps P-101 to P-106 | Electrical | 2026-08-25 | 2026-09-02 | L5
L6-ELEC-3351 | Pull LV cable feeder F-01 MCC-B to DB-7A | Electrical | 2026-08-15 | 2026-08-17 | L6
L6-ELEC-3352 | Pull LV cable feeder F-02 MCC-B to DB-7B | Electrical | 2026-08-17 | 2026-08-19 | L6
L6-ELEC-3353 | Terminate cable feeder F-01 at MCC-B | Electrical | 2026-08-19 | 2026-08-20 | L6
L6-ELEC-3354 | Terminate cable feeder F-01 at DB-7A | Electrical | 2026-08-20 | 2026-08-21 | L6
L6-ELEC-3355 | Megger test feeder F-01 MCC-B to DB-7A | Electrical | 2026-08-21 | 2026-08-21 | L6
L6-ELEC-3356 | Install earthing strip MCC room B north wall | Electrical | 2026-08-22 | 2026-08-23 | L6
L6-ELEC-3357 | Install earthing strip MCC room B south wall | Electrical | 2026-08-23 | 2026-08-24 | L6
L6-ELEC-3358 | Connect equipment earth bonds MCC-B panel P1 to P6 | Electrical | 2026-08-24 | 2026-08-25 | L6
L6-ELEC-3359 | Earth continuity test MCC room B all equipment | Electrical | 2026-08-25 | 2026-08-26 | L6
L6-ELEC-3360 | Pre-commissioning checks MCC-B incomer panel | Electrical | 2026-09-01 | 2026-09-02 | L6
L5-INST-4401 | Instrument cable tray installation Unit 5 | Instrumentation | 2026-08-10 | 2026-08-18 | L5
L5-INST-4402 | Instrument cable pulling Unit 5 field instruments | Instrumentation | 2026-08-18 | 2026-08-26 | L5
L5-INST-4403 | Instrument cable termination field junction boxes Unit 5 | Instrumentation | 2026-08-26 | 2026-09-02 | L5
L5-INST-4404 | Control valve installation Unit 5 process lines | Instrumentation | 2026-08-15 | 2026-08-22 | L5
L5-INST-4405 | Flow transmitter installation Unit 5 | Instrumentation | 2026-08-20 | 2026-08-26 | L5
L5-INST-4406 | Pressure transmitter installation Unit 5 | Instrumentation | 2026-08-20 | 2026-08-26 | L5
L5-INST-4407 | Temperature element installation Unit 5 | Instrumentation | 2026-08-22 | 2026-08-28 | L5
L5-INST-4408 | DCS marshalling cabinet installation control room | Instrumentation | 2026-08-05 | 2026-08-12 | L5
L5-INST-4409 | Loop testing field instruments to DCS Unit 5 | Instrumentation | 2026-09-01 | 2026-09-08 | L5
L5-INST-4410 | Functional testing control valves Unit 5 | Instrumentation | 2026-09-05 | 2026-09-10 | L5
L6-INST-4451 | Install flow transmitter FT-5101 on line 6-PL-0012 | Instrumentation | 2026-08-20 | 2026-08-21 | L6
L6-INST-4452 | Install pressure transmitter PT-5102 Unit 5 north | Instrumentation | 2026-08-21 | 2026-08-22 | L6
L6-INST-4453 | Install temperature element TE-5103 reactor inlet | Instrumentation | 2026-08-22 | 2026-08-23 | L6
L6-INST-4454 | Install control valve CV-5104 on line 12-PL-0018 | Instrumentation | 2026-08-23 | 2026-08-24 | L6
L6-INST-4455 | Pull instrument cable IC-5101 from FT-5101 to JB-51A | Instrumentation | 2026-08-24 | 2026-08-25 | L6
L6-INST-4456 | Terminate instrument cable IC-5101 at JB-51A | Instrumentation | 2026-08-25 | 2026-08-26 | L6
L6-INST-4457 | Loop test FT-5101 to DCS channel AI-5101 | Instrumentation | 2026-09-01 | 2026-09-01 | L6
L6-INST-4458 | Loop test PT-5102 to DCS channel AI-5102 | Instrumentation | 2026-09-01 | 2026-09-01 | L6
L6-INST-4459 | Functional test CV-5104 open close and modulating | Instrumentation | 2026-09-05 | 2026-09-05 | L6
L6-INST-4460 | Calibration check PT-5102 against reference gauge | Instrumentation | 2026-08-22 | 2026-08-22 | L6
L5-HSE-5501 | Site boundary fencing and gate installation | HSE | 2026-07-25 | 2026-08-02 | L5
L5-HSE-5502 | Temporary fire water network installation site | HSE | 2026-08-01 | 2026-08-10 | L5
L5-HSE-5503 | Emergency assembly point setup and signage | HSE | 2026-08-02 | 2026-08-04 | L5
L5-HSE-5504 | HSE induction training all new site workers | HSE | 2026-08-01 | 2026-09-30 | L5
L5-HSE-5505 | Safety signage installation all work zones | HSE | 2026-08-03 | 2026-08-08 | L5
L5-HSE-5506 | First aid station setup and stocking site | HSE | 2026-08-01 | 2026-08-03 | L5
L5-HSE-5507 | Permit to work system implementation and audit | HSE | 2026-08-05 | 2026-08-10 | L5
L5-HSE-5508 | Fire extinguisher deployment all work areas | HSE | 2026-08-03 | 2026-08-06 | L5
L5-HSE-5509 | Weekly HSE inspection all active work zones | HSE | 2026-08-07 | 2026-09-30 | L5
L5-HSE-5510 | Excavation safety and shoring inspection Unit 5 and 6 | HSE | 2026-08-03 | 2026-08-30 | L5
L6-HSE-5551 | Toolbox talk confined space entry Unit 5 vessels | HSE | 2026-08-20 | 2026-08-20 | L6
L6-HSE-5552 | Toolbox talk working at height Unit 7 pipe rack | HSE | 2026-09-01 | 2026-09-01 | L6
L6-HSE-5553 | Hot work permit inspection welding zone Unit 5 | HSE | 2026-08-12 | 2026-08-12 | L6
L6-HSE-5554 | Hot work permit inspection welding zone Unit 6 | HSE | 2026-08-19 | 2026-08-19 | L6
L6-HSE-5555 | Near miss investigation report Unit 5 scaffold incident | HSE | 2026-08-15 | 2026-08-16 | L6
L6-HSE-5556 | PPE compliance audit all civil workers Unit 7 | HSE | 2026-09-02 | 2026-09-02 | L6
L6-HSE-5557 | Fire watch duty during hot work north pipe rack | HSE | 2026-09-01 | 2026-09-06 | L6
L6-HSE-5558 | Barricading and signage excavation pit grid B Unit 6 | HSE | 2026-08-13 | 2026-08-13 | L6
L6-HSE-5559 | Emergency drill evacuation all personnel site | HSE | 2026-08-28 | 2026-08-28 | L6
L6-HSE-5560 | Scaffolding inspection certificate Unit 7 pipe rack | HSE | 2026-08-31 | 2026-08-31 | L6

## Summary
Discipline | L5 Count | L6 Count | Total
Civil | 20 | 10 | 30
Piping | 10 | 10 | 20
Electrical | 10 | 10 | 20
Instrumentation | 10 | 10 | 20
HSE | 10 | 10 | 20
TOTAL | 60 | 50 | 110